## Sheet1
Risk Table | Karl Lois A. Gerarcas | Group 8 | Pinoy Beer Bottle Brewery Inc.
Risk | Category | Probability | Impact | RE | Pointer to RMMM
staff turnover will be high | Staff size & experience | 40% | 3 | 32000 |  | 80000
Electrical Failure on the System | Developement Environment | 10% | 1 | 8000 |  | 80000
poor communication with the customer | business impact | 55% | 2 | 8000 |  | 20000
dilution of staff effort as ongoing maintenance requests are serviced | Staff size & experience | 30% | 2 | 30000 |  | 100000
larger number of users than planned | Project size | 60% | 2 | 4000 |  | 10000
unstable anti-virus/malware software that protects the Machines | technology | 10% | 2 | 5000 |  | 50000
Delivery deadline will be tightened | business impact | 20% | 3 | 2000 |  | 5000
Funding will be lost | business impact | 70% | 2 | 70000 |  | 100000
Cutomer will change requirements | customer characteristics | 50% | 4 | 32000 |  | 80000
Technology will not meet expectations | technology | 40% | 3 | 60000 |  | 150000
staff inexperienced | Staff size & experience | 60% | 4 | 12000 |  | 30000
lack of training on tools | technology | 60% | 4 | 60000 |  | 100000
Computer Memory Shortage | technology | 20% | 2 | 60000 |  | 150000